## Start here
Agency resource planning template
Plan your people across every project for the next 12 weeks, with tentative work weighted by its chance of winning, and a project timeline.
How to use it
1. Settings: set the Monday your plan starts, hours per day and the example thresholds.
2. People: list each person, their role and their hours per week. Add leave in days on the Leave tab.
3. Projects: list projects with a status. Give tentative work (pitches, proposals) a win probability.
4. Plan: one row per person and project, with hours per week for the next 12 weeks.
5. Resource plan and Project timeline: check who is over or under, and when each project needs people.
Colour key
Pale yellow cells are yours to edit. Everything else calculates.
The example data is invented. To start your own plan, delete the yellow cells on the input tabs; the formulas stay.
Sheets are protected without a password so formulas aren't overwritten by accident. Review > Unprotect sheet if you want to change them.
Weighted tentative hours = tentative hours × win probability. Confirmed work always counts at 100%.
Made with Kavaro
Kavaro: resource management software for agencies and consultancies.
Template page and latest version: kavaro.io/templates/agency-resource-planning-template
Licence: free to use, share and adapt, including on your own site, as long as you credit Kavaro with a link to the template page (CC BY 4.0).
Keep your resource plan live, not in a spreadsheet: try Kavaro free

## Settings
Settings
First week commencing | 2026-11-02
Hours per day | 7.5
Over-booked above | 100% | Example thresholds; set your own. % booked counts confirmed hours plus weighted tentative hours.
Under-booked below | 60%

## People
People (up to 60)
Name | Role | Hours per week
Asha | Designer | 37.5
Ben | Designer | 37.5
Cleo | Designer | 22.5
Eli | Developer | 37.5
Femi | Developer | 37.5
Isla | Project manager | 37.5
Kit | Strategist | 30
Lena | Account manager | 37.5

## Leave
Leave, in days per week (names come from the People tab)
Name
5
2
3

## Projects
Projects (up to 40)
Project | Client | Status | Win probability | Probability used | Confirmed work counts at 100%. Give tentative work (pitches, proposals, likely extensions) a win probability.
Northwind rebrand | Northwind | Confirmed
Harbour app build | Harbour | Confirmed
Lumen retainer | Lumen | Confirmed
Orbit website (pitch) | Orbit | Tentative | 50%
Atlas campaign (proposal) | Atlas | Tentative | 40%

## Plan
Plan: hours per person, per project, per week (up to 300 rows)
Person | Project | Status | Probability | [12 empty] | Row total
Asha | Northwind rebrand |  |  | 25 | 25 | 25 | 25 | 25 | 25
Asha | Lumen retainer |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Asha | Orbit website (pitch) | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Ben | Northwind rebrand |  |  | 20 | 20 | 20 | 20 | 20 | 20
Ben | Atlas campaign (proposal) | [8 empty] | 15 | 15 | 15 | 15 | 15 | 15
Cleo | Lumen retainer |  |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Eli | Harbour app build |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
Eli | Orbit website (pitch) | [8 empty] | 15 | 15 | 15 | 15 | 15 | 15
Femi | Harbour app build |  |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Femi | Lumen retainer |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Isla | Northwind rebrand |  |  | 8 | 8 | 8 | 8 | 8 | 8
Isla | Harbour app build |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Isla | Lumen retainer |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Isla | Orbit website (pitch) | [6 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Isla | Atlas campaign (proposal) | [8 empty] | 4 | 4 | 4 | 4 | 4 | 4
Kit | Northwind rebrand |  |  | 10 | 10 | 10 | 10
Kit | Lumen retainer |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Kit | Atlas campaign (proposal) | [8 empty] | 10 | 10 | 10 | 10 | 10 | 10
Lena | Northwind rebrand |  |  | 10 | 10 | 10 | 10 | 10 | 10
Lena | Lumen retainer |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Lena | Atlas campaign (proposal) | [8 empty] | 8 | 8 | 8 | 8 | 8 | 8

## Resource plan
Resource plan: each person's available and booked hours, by week
Person | Measure
Agency total | Available
Confirmed
Tentative
Weighted tentative
% booked (confirmed + weighted)
Status

## Project timeline
Project timeline: hours each project needs, by week (shaded weeks have work booked) | [6 empty] | Helper: week numbers with hours
Project | Status | Probability | Total hours | Weighted hours | First week | Last week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12