## Start here
Capacity planning template for agencies
Weekly capacity vs booked and tentative work, by role, for the next 12 weeks.
How to use it
1. Settings: set the Monday your plan starts, working days per week, and your roles.
2. Team: list each person with their role, contracted hours and the share of time that never goes on project work.
3. Time off: enter days off per person per week (holidays, sick leave, training away from work).
4. Work: add confirmed projects and tentative work (pitches, proposals, likely extensions) as hours per role per week.
5. Capacity vs booked: read each role's free hours and % booked. Red = over-booked, amber = near capacity, grey = bench risk.
Colour key
Pale yellow cells are yours to edit. Everything else calculates.
The example data is invented. To start your own plan, delete the yellow cells on the input tabs; the formulas stay.
Sheets are protected without a password so formulas aren't overwritten by accident. Review > Unprotect sheet if you want to change them.
Made with Kavaro
Kavaro: resource management software for agencies and consultancies.
Template page and latest version: kavaro.io/templates/capacity-planning-template
Licence: free to use, share and adapt, including on your own site, as long as you credit Kavaro with a link to the template page (CC BY 4.0).
See next quarter's capacity by role, live: try Kavaro free

## Settings
Settings
First week commencing | 2026-11-02
Number of weeks | 12 | Fixed at 12 week columns in this file.
Working days per week | 5
Over-booked above | 100% | Example thresholds; set your own.
Near capacity above | 85%
Under-booked below | 60%
Roles or teams (up to 12)
Design
Development
Project management
Strategy

## Team
Team (one row per person, up to 60) |  |  | Non-project time %: the share of time that never goes on project work (meetings, admin, internal work). |  |  | Available hours, calculated (week commencing). Time off comes off first, then the non-project share.
Name | Role or team | Contracted hours per week | Non-project time % | Start date (optional) | End date (optional)
Asha | Design | 37.5 | 15%
Ben | Design | 37.5 | 15%
Cleo | Design | 30 | 15%
Dami | Design | 37.5 | 15%
Eli | Development | 37.5 | 15%
Femi | Development | 37.5 | 15%
Gus | Development | 37.5 | 15%
Hana | Development | 37.5 | 15%
Isla | Project management | 37.5 | 25%
Jon | Project management | 37.5 | 25%
Kit | Strategy | 37.5 | 30%
Lena | Strategy | 37.5 | 30%

## Time off
Time off, in days per week (names come from the Team tab)
Name
5
2
3
1

## Work
Work: hours needed from each role per week (up to 100 rows) |  |  |  |  | Tentative = pitches, proposals and likely extensions.
Project | Client | Role or team | Status
Northwind rebrand | Northwind | Design | Confirmed | 60 | 60 | 60 | 60 | 60 | 60
Northwind rebrand | Northwind | Strategy | Confirmed | 15 | 15 | 15 | 15
Northwind rebrand | Northwind | Project management | Confirmed | 10 | 10 | 10 | 10 | 10 | 10
Harbour app build | Harbour | Development | Confirmed | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Harbour app build | Harbour | Design | Confirmed | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Harbour app build | Harbour | Project management | Confirmed | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Lumen retainer | Lumen | Design | Confirmed | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Lumen retainer | Lumen | Development | Confirmed | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Lumen retainer | Lumen | Strategy | Confirmed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Lumen retainer | Lumen | Project management | Confirmed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Orbit website (pitch) | Orbit | Design | Tentative |  |  | 40 | 40 | 40 | 40 | 40 | 40
Orbit website (pitch) | Orbit | Development | Tentative |  |  |  |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
Orbit website (pitch) | Orbit | Project management | Tentative |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10

## Capacity vs booked
Capacity vs booked, by role and week
Role or team | Measure
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status
Agency total | Capacity
Confirmed
Tentative
Free
% booked (confirmed only)
% booked incl. tentative
Status