## Start here
Project staffing plan template
The roles one project needs, week by week, who fills each seat, what's still open, and whether it fits the budget. A project plan, not an HR headcount plan.
How to use it
1. Project: name the project, set the Monday it starts, the number of weeks and the budget. Add phases in week order.
2. Staffing plan: one row per seat. Add the role, the skills it needs, and mark it Named, Open or Freelance.
3. Enter the hours each seat needs every week (from the scope or SOW).
4. Summary: check people needed at peak, open-seat hours and the first week an open seat is needed.
5. Budget: add a day rate per role and check the fee against the budget.
Colour key
Pale yellow cells are yours to edit. Everything else calculates.
The example data is invented. To start your own plan, delete the yellow cells on the input tabs; the formulas stay.
Sheets are protected without a password so formulas aren't overwritten by accident. Review > Unprotect sheet if you want to change them.
Made with Kavaro
Kavaro: resource management software for agencies and consultancies.
Template page and latest version: kavaro.io/templates/project-staffing-plan-template
Licence: free to use, share and adapt, including on your own site, as long as you credit Kavaro with a link to the template page (CC BY 4.0).
Turn your next SOW into a staffing plan: try Kavaro free

## Project
Project
Project name | Harbour app build
Client | Harbour Ltd
First week commencing | 2026-11-02
Number of weeks (up to 26) | 16 | The file has 26 week columns. Weeks past this number grey out and drop out of the totals.
Standard full-time hours per week | 37.5
Hours per day | 7.5
Currency | £ | Number format only: no conversion.
Budget (fee) | 150000
Phases (up to 8, in week order)
Phase | First week | Last week
Discovery | 1 | 2
Design | 3 | 6
Build | 7 | 14
Launch | 15 | 16

## Staffing plan
Staffing plan: hours each seat needs, by week
Phase
|  |  |  | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
|  |  |  | Week commencing | [29 empty] | Helper: week numbers with hours (used for first and last week)
Role | Seniority | Skills needed | Fill status | Person | [26 empty] | Total hours | First week | Last week
Project manager | Senior | Agile delivery, client reporting | Named | Isla | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Strategist | Senior | Research, workshops | Named | Kit | 20 | 20 | 5 | 5 | 5 | 5
UX designer | Mid | User research, prototyping | Named | Asha | 20 | 20 | 37.5 | 37.5 | 37.5 | 37.5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
UI designer | Mid | Design systems, accessibility | Open |  |  |  | 37.5 | 37.5 | 37.5 | 37.5 | 10 | 10 | 10 | 10
Senior developer | Senior | React Native, API design | Named | Eli |  |  | 10 | 10 | 10 | 10 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5
Developer | Mid | React Native, accessibility | Open | [7 empty] | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 20 | 20
QA tester | Mid | Device testing, test plans | Freelance | [12 empty] | 20 | 20 | 20 | 20 | 20
Weekly total
People needed (full-time equivalent)
Open-seat hours

## Summary
Summary
Total hours
Peak weekly hours
Peak starts in week
Peak ends in week
People needed at peak
Open-seat hours
First week an open seat is needed
Seats
Open seats
Helper: weeks at peak
Helper: weeks with an open seat
Role hours by week (helper)
Role (from the Budget tab) | Total hours | Peak weekly hours | People needed at peak | Days

## Budget
Budget: fee check using a day rate per role
Need a rate card? Use our agency rate card template: kavaro.io/templates/agency-rate-card-template
Role | Day rate (example rates) | Hours | Days | Fee
Project manager | 600
Strategist | 900
UX designer | 650
UI designer | 600
Senior developer | 750
Developer | 550
QA tester | 450
Roles not listed here don't get a fee. Add every role used on the Staffing plan tab. |  |  | Total fee
Budget
Budget minus fee
Result