## Start here
Resource allocation template for agencies
Allocate people to projects by week, in hours, and flag anyone over-allocated, under-allocated or booked while on holiday.
How to use it
1. Settings: set the Monday your plan starts and your over- and under-allocation thresholds.
2. People: list each person, their role and their hours per week.
3. Projects: list projects with a status (Confirmed or Tentative). Internal and Time off are reserved rows.
4. Allocations: one row per person and project, with hours per week. Put holidays on the Time off project: they reduce availability.
5. Person load: fix every Over and Booked while off cell before the week starts. Project load shows hours by project.
Colour key
Pale yellow cells are yours to edit. Everything else calculates.
The example data is invented. To start your own plan, delete the yellow cells on the input tabs; the formulas stay.
Sheets are protected without a password so formulas aren't overwritten by accident. Review > Unprotect sheet if you want to change them.
Think in percentages? 50% of a 37.5-hour week is 18.75 hours. The grid uses hours only: mixing % and hours is the most common way these sheets break.
Made with Kavaro
Kavaro: resource management software for agencies and consultancies.
Template page and latest version: kavaro.io/templates/resource-allocation-template
Licence: free to use, share and adapt, including on your own site, as long as you credit Kavaro with a link to the template page (CC BY 4.0).
Allocate your team on a live schedule: try Kavaro free

## Settings
Settings
First week commencing | 2026-11-02
Over-allocated above | 100% | Example thresholds; set your own. Over means strictly above this.
Under-allocated below | 70%

## People
People (up to 60)
Name | Role | Hours per week
Asha | Designer | 37.5
Ben | Designer | 37.5
Cleo | Designer | 22.5
Eli | Developer | 37.5
Femi | Developer | 37.5
Isla | Project manager | 37.5

## Projects
Projects (Internal and Time off are reserved rows)
Project | Client | Status | Billable
Internal |  | Confirmed | No
Time off |  | Not work: reduces availability
Northwind rebrand | Northwind | Confirmed | Yes
Harbour app build | Harbour | Confirmed | Yes
Lumen retainer | Lumen | Confirmed | Yes
Orbit website (pitch) | Orbit | Tentative | No

## Allocations
Allocations: hours per person, per project, per week (up to 300 rows) |  |  |  | Think in percentages? 50% of a 37.5-hour week is 18.75 hours. Use hours only.
Person | Project | Status | [12 empty] | Row total
Asha | Northwind rebrand |  | 30 | 30 | 30
Asha | Lumen retainer |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Asha | Time off |  |  |  |  | 37.5
Ben | Northwind rebrand |  | 20 | 20
Ben | Orbit website (pitch) |  |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Ben | Internal |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Eli | Harbour app build |  | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5
Eli | Lumen retainer |  | 8 | 8
Femi | Harbour app build |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Femi | Time off |  | 15
Isla | Harbour app build |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Isla | Northwind rebrand |  | 10 | 10 | 10 | 10
Isla | Lumen retainer |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Isla | Orbit website (pitch) |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Cleo | Lumen retainer |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15

## Person load
Person load: available vs allocated hours, by week
Person | Measure

## Project load
Project load: hours by project and week
Project | Status
Confirmed total
Tentative total
Time off total